## Slide 1
Project Management and Vendor Development
NOIDA INSTITUTE OF ENGINEERING & TECHNOLOGY GREATER NOIDA
By
Priya Bharti
Assistant Professor
MBA
NIET, GREATER NOIDA
Lecture – 1 Topic: Project Identification & Selection
Market & Demand Analysis Project Risk

## Slide 2: Index
S No | Content
1 | Name of Subject with code, Course and Subject Teacher
2 | Brief Introduction of Faculty member with Photograph
3 | Evaluation Scheme
4 | Syllabus
5 | Branch wise Application
6 | Course Objective(s)
7 | Course Outcome(s)
8 | Program Outcomes (POs)
9 | COs and POs Mapping
10 | Program Educational Objectives (PEOs)
11 | Result Analysis
12 | End Semester Question paper Templates
13 | Prequisite/Recap

## Slide 3: Index
S No | Content
14 | Brief Indtroduction about the Subject with Videos
15 | Unit Content
16 | Unit Objectives
17 | Topic Objectives & Topic Outcome
18 | Lecture related to topic
19 | Daily Quiz
20 | Weekly Assignment
21 | Topic Links
22 | MCQs
23 | Glossary Questions
24 | Old question papers
25 | Expected Questions
26 | Recap of unit

## Slide 4: Brief Introduction of the Faculty Member
Faculty Name: Priya Bharti
Designation: ASSISTANT PROFESSOR
Department: MBA
Email ID: shrutisharma@niet.co.in
Qualification: MBA (pursuing PHD.)
Specialization: Finance & Human Resource Management
Research Area: Entrepreneurship and innovation
Teaching Area: Management (Finance & Core subjects)
Total Experience: 3.5 years

## Slide 5: Evaluation Scheme

## Slide 6: Syllabus

## Slide 7: Syllabus

## Slide 8: Branch Wise Application
Handling projects.
Evaluating & Monitoring Project Process
Taking necessary and corrective action.

## Slide 9: Course objective(s)
To empower the students to get insights of basic concepts on project management.
To create awareness on the roles and responsibilities of project manager.
To build the confident among the students to take up any kind of projects.
To sharpen the planning, scheduling and controlling skills of the students with respect to individual projects.
To understand the perspectives in which optimum decisions are to be taken in case of risks with planned activities in project.

## Slide 10: Course outcome(s)
CO 1 | Understand the basic concepts and characteristics of Project and Project manager, management | Understanding (K2)
CO 2 | Understand the roles and responsibilities along with tools & techniques used in Project Management | Evaluating (K5)
CO 3 | Develop confident to take up any kind of projects | Evaluating (K5)
CO 4 | Students will understand the scheduling and monitoring process in Project. They will be able to apply PERT and CPM method for project scheduling | Applying (K3)
CO 5 | Students will understand the perspectives in which optimum decisions are to be taken in case of risks with planned activities in project | Creating (K6)

## Slide 11: Program outcome (POs)
PO1. Apply knowledge of management theories and practices to solve business problems.
PO2. Foster analytical and critical thinking abilities for data-based decision-making.
PO3. Ability to develop value-based leadership ability.
PO4. Ability to understand, analyze, and communicate global, economic, legal, and ethical aspects of business.
PO5. Ability to lead themselves and others in the achievement of organizational goals, contributing effectively to a team environment.

## Slide 12: COs and POs Mapping
*1=High, *2=Medium, *3=Low

## Slide 13: Program Educational Objectives (PEOs)
PEO 1: Graduates of the management program will have conceptual knowledge, to adapt to the rapidly changing environment, learn new skills and demonstrate application of management principles in a professional work setting.
PEO 2: Graduates will apply appropriate tools for decision making required for solving complex managerial problems in the local or global context.
PEO 3: Graduates of the management program will exhibit integrity, social responsibility, and teamwork.
PEO 4: Graduates will exhibit ethics, communication skills, leadership qualities and entrepreneurial mindset using creativity and innovation.

## Slide 14: Result Analysis

## Slide 15: End Semester Question paper Templates

## Slide 16: End Semester Question paper Templates

## Slide 17: Prerequisite /Recap
Prerequisites for this session are:
General understanding of project management.
General understanding of tools & techniques of project management.
Recap:
Introduction of project
Project management process
Project team
Scope of project management

## Slide 18: Brief Introduction about the Subject with Videos
Project management is the discipline of initiating, planning, executing, controlling, and closing the work of a team to achieve specific goals and meet specific success criteria.
It involves the application of knowledge, skills, tools, and techniques to project activities to meet project requirements.
Effective project management ensures that projects are completed within scope, on time, and within budget, while delivering the desired outcomes.
https://www.youtube.com/watch?v=EyPFi0YO32M
https://www.youtube.com/watch?v=BOU1YP5NZVA

## Slide 19: Unit Content
Unit-2:
Project Identification & Selection:
Identification, Generation of Ideas, Approaches to Project Screening and Selection, Project Rating Index.
Market & Demand Analysis Techniques: Survey & Trend Projection Methods.
Project Risk Management: Concepts and Types of Project Risks, Risk Identification, Risks Analysis, Risks Mitigation Strategies.

## Slide 20: Unit objective
Objectives of this unit are:
To understand how projects are identified and selected.
To understand and conduct the market and demand analysis
To manage the project risks about risk identification, risk analysis and mitigation strategies

## Slide 21: Topic Objectives & Topic Outcome
S.NO | TOPIC OBJECTIVE | TOPIC OUTCOME
1 | To understand the Identification & Generation of ideas. | CO2

## Slide 22: Idea Generation & Sources
Identifying prospective investment opportunities that offer good commercial returns or satisfy strategic goals.
Key Sources of Ideas:
  Internal Sources: R&D departments, employee suggestions, operational bottlenecks.
  External Sources: Market demand analysis, customer pain points, competitor analysis, government policies/incentives.
Techniques for Idea Generation:
  Brainstorming: Group idea creation without immediate criticism.
  Delphi Technique: Expert consensus obtained through iterative rounds of anonymous questionnaires.
  SWOT Analysis: Leveraging organizational Strengths and Opportunities while guarding against Weaknesses and Threats.

## Slide 23: Comparative Rating & Screening Approaches
Objective of Screening: Quickly eliminate non-viable ideas before spending high capital on detailed feasibility reports.
Approaches to Screening:
  Unpromising Idea Elimination: Filtering out ideas incompatible with organizational capability or regulatory boundaries.
  Comparative Rating Matrix: Evaluating multiple product ideas against a set of key factors on a numerical scale.

## Slide 24: Example
Criterion | Weight (Wi​) | Project A Score (SA​) | Project B Score (SB​) | Product A Weighted | Product B Weighted
Market Demand | 0.35 | 4 | 5 |  | 
Tech Feasibility | 0.30 | 5 | 3 |  | 
Raw Material | 0.15 | 3 | 4 |  | 
Financial Return | 0.20 | 4 | 3 |  | 
Total | 1.00 | — | — | 4.15 | 3.85
Criterion | Weight (Wi​) | Project A Score (SA​) | Project B Score (SB​) | Product A Weighted | Product B Weighted
Market Demand | 0.35 | 4 | 5 |  | 
Tech Feasibility | 0.30 | 5 | 3 |  | 
Raw Material | 0.15 | 3 | 4 |  | 
Financial Return | 0.20 | 4 | 3 |  | 
Total | 1.00 | — | — | 4.15 | 3.85
Product A is preferred due to higher technical feasibility and overall score.

## Slide 25: Project feasibility and Pre-feasibility report
Pre-Feasibility Report: A preliminary, coarse evaluation of a project concept. It determines whether to commit funds to a full-fledged Feasibility Study.
Full Feasibility Study: A comprehensive, multi-dimensional evaluation covering four main pillars.

## Slide 26: Project feasibility and Pre-feasibility report
The 4 Stages of Feasibility Analysis
1. Market Feasibility
Demand Estimation: Past consumption trends, market share projections.
Supply & Competition: Existing plant capacities, import/export scenarios.
Pricing & Distribution: Price elasticity, marketing channels, sales force requirements.
2. Technical Feasibility
Manufacturing Process: Selection of appropriate technology/equipment.
Plant Capacity & Location: Economies of scale, proximity to raw materials, logistics, availability of power and water.
Civil Works & Layout: Floor planning, environmental waste handling infrastructure.

## Slide 27: Project feasibility and Pre-feasibility report
3. Financial Feasibility
Capital Cost: Land, building, plant & machinery, working capital requirement.
Operating Cost: Raw material, labor, energy, maintenance.
Financial Evaluation Metrics:
  Net Present Value (NPV)
  Internal Rate of Return (IRR)
  Payback Period
  Debt Service Coverage Ratio (DSCR)
4. Social Cost-Benefit Analysis (SCBA)
Purpose: Evaluates project impact on society and national economy (crucial for public sector projects).
Key Factors:
  Employment Generation: Direct and indirect job creation.
  Shadow Pricing: Adjusting market prices to reflect true social value (e.g., social cost of pollution, social benefit of foreign exchange savings).
  Regional Development: Impact on backward regions.

## Slide 28: Project Selection & Project Rating Index
Project Rating Index (PRI)
Concept: A quantitative evaluation technique used to rank competing project proposals based on weighted evaluation factors.
Formula:
Where:
= Weight assigned to factor (such that )
= Score assigned to the project for factor (typically on a 1-to-5 or 1-to-7 scale)
= Total number of evaluation criteria

## Slide 29: Numerical
Problem Statement: An engineering firm is evaluating a new manufacturing unit project across 4 criteria. Calculate the Project Rating Index () and determine if the project passes the threshold score of .
Criteria Weights ():
  Technical Feasibility =
  Market Potential =
  Financial Returns =
  Environmental Safety =
Assigned Scores (, Scale 1 to 5):
  Tech Feasibility =
  Market Potential =
  Financial Returns =
  Environmental Safety =

## Slide 30: Numerical
Calculation:
Decision: Since , the project meets the benchmark and qualifies for selection

## Slide 31: Project Identification
Requires:
Imagination
Sensitivity to Environmental Changes
Realistic assessment of what the firm can do

## Slide 32: Stimulation of Flow of Ideas
SWOT analysis

## Slide 33: Stimulation of Flow of Ideas
Clear Articulation of Objectives:
The operational objectives of the firm can be one or more of following:
Cost Reduction
Productivity Improvement
Increase in Capacity Utilization
Improvement in Contribution Margin
Expansion into Promising Fields

## Slide 34: Stimulation of Flow of Ideas
Fostering a Conducive Climate:
To tap the creativity of the people and to harness their entrepreneurial urges, a conducive organizational climate has to be fostered.

## Slide 35: Tools for Identifying Project Opportunities
Porter Model
Life Cycle Approach
The Experience Curve

## Slide 36: 1. Porter’s 5 Forces

## Slide 37: 2. Life cycle approach
Pioneering Stage (-ve NPV)
Rapid Growth Stage (+ve NPV)
Maturity & Stabilization Stage (Neutral)
Decline Stage (-ve NPV)

## Slide 38: 3. Experience curve

## Slide 39: Generating Project Ideas
Analyze the performance of existing industries
Examine inputs & outputs of various industries
Review imports & exports
Study plan outlay & Government guidelines
Investigate local materials & resources
Analyze economic & social trends

## Slide 40: Generating Project Ideas
Study new technological developments
Draw clues from consumption abroad
Explore the possibility of reviving sick units
Identify unfulfilled psychological needs
Attend trade fairs
Stimulate creativity for generating new ideas

## Slide 41: Project Implementation Stages
Project Initiation & Approvals: Securing statutory clearances, land acquisition, funding sign-offs.
Detailed Engineering & Design: Finalizing blueprints, technical specifications, and purchase descriptions.
Procurement & Contracting: Issuing RFPs/Tenders, vendor selection, contract negotiation.
Construction & Erection: Civil works, equipment installation, site assembly.
Testing & Commissioning: Dry runs, performance testing, quality validation.
Handover: Commercial operations date (COD), transferring control to operations team.

## Slide 42: Topic objective and topic outcome
s.no. | topic | CO
1 | To learn the Approaches to Project Screening and Selection & Project Rating Index | CO2

## Slide 43: Project Screening & Selection
  Some kind of preliminary screening is required to eliminate ideas that prima facie are not promising, The Following aspects may be looked into:
  Compatibility with the promoter
  Consistency with Government priorities
  Availability of inputs
  Adequacy of market
  Reasonableness of cost
  Acceptability of risk level

## Slide 44: 1. Compatibility with the promoter
The idea must be compatible with the interest, personality & resources of an entrepreneur:
Real Opportunity has three characteristics (Murphy)
It fits the personality of the entrepreneur- it squares with his abilities, training & proclivities
It is accessible to him
It offers him the prospects of rapid growth & high return on invested capital

## Slide 45: 2. Consistency with Government priorities
Questions to be raised in this context are:
Is the project consistent with national goals & priorities?
Are there any environmental effects contrary to Government regulations?
Can the foreign exchange requirement of the project can be easily accommodated?
Will there be any difficulty in obtaining the license for the project?

## Slide 46: 3. Availability of inputs
Power (Electric, diesel, coal)
Foreign Exchange
Important Raw Material
Supplies of Agricultural Products

## Slide 47: 4. Adequacy of market
The following factors have to be analyzed.
  Total present domestic market
  Competitors & their market share
  Quality-Price profile
  Sales & distribution system
  Barriers to the entry of new units
  Economic, social & demographic trends
  Patent protection

## Slide 48: 5. Reasonableness of Cost
The cost structure the project must enable it to realise an acceptable profit with a price.
Cost of material inputs
Labor cost
Factory overheads
General administration expenses
Selling & distribution costs
Services costs

## Slide 49: 6. Acceptability of risk level
In the assessment of risk the following factors should be considered:
Vulnerability of business cycle
Technological changes
Competition from substitutes
Competition from imports
Shifts in consumer preferences

## Slide 50: Project Rating Index (PRI)
When a firm evaluates a large number of project ideas, it may be helpful to streamline the process of preliminary screening. For this purpose, a preliminary evaluation may be translated into a Project Rating Index.

## Slide 51: Steps of PRI
Identify factors relevant for project rating.
Assign weights to these factors. (Subject to their relative importance)
Rate the project proposal on various factors, using a suitable rating scale. (5 point scale)
For each factor, multiply the factor rating with the factor weight to get the factor score
Add all the factors scores to get the overall project rating index

## Slide 52: Ranking Potential Projects
Ease of implementation
Estimated resource hours
Estimated timescale
Estimated level of resistance
Number of cross-teams impacted
Other considerations
Alignment to strategy
Sustain/develop client focus
Quality policy
Capital required
Scale of Benefit
Size of the opportunity
Money saved
Cost avoidance
Time saved
Repeatable benefit

## Slide 53: Using Priority Matrix
S.No. | Criteria | Weight (W) | Score (S) | Weighted score
1 | Organisational alignment | 25% |  | W*S
2 | Projected benefits 2.1 External customers 2.2 External stakeholders 2.3 Employee or internal customer 2.4 Other(community/environment) | 20% |  | 
3 | Resources required | 15% |  | 
4 | Scope in terms of required returns | 15% |  | 
5 | Clarity of deliverables | 10% |  | 
6 | Time to complete | 10% |  | 
7 | Team membership requirements | 5% |  | 
 | Total weighted score | 100% |  | 

## Slide 54: Topic Objectives & Outcome
s.no. | topic | outcomes
1 | To understand conducting the Market & Demand Analysis Techniques: | CO2

## Slide 55: Market & Demand Analysis
Market & Demand analysis is concerned with two broad issues:
What is the likely aggregate demand for the product?
What share of the market will the proposed project enjoy?

## Slide 56: Factors, that answer >
Patterns of consumption
Income & Price elasticity of demand
Composition of market
Nature of competition
Availability of substitutes
Reach of distribution channel

## Slide 57: Collection of Secondary Information
Census of India
National Sample Survey Report
Plan Reports
Statistical Abstracts of Indian Union
India Year Book (Ministry of Info & Broad )
Statistical Year Book (United Nations)
Economic Survey (Ministry of Finance)
Guidelines to Industries (Min of Industrial Dev)
Annual Survey of Industries (CSO)

## Slide 58: Conduct of Survey
Define the Target Population
Select the Sample & Sampling Technique
Develop the Questionnaire
Recruit & Train the Field Advisors
Obtain Information as Per Questionnaire
Scrutinize the Information Gathered
Analyze & Interpret the Information

## Slide 59: Characterization of Market
Effective demand in the past & present
Breakdown of demand
Price
Methods of distribution & sales promotion
Consumers
Supply & competition
Government Policy

## Slide 60: Marketing Strategy
Target Segment
Positioning
Product Line
Price
Distribution
Sales Force
Sales Promotion
Advertising
Notes: Sales force: a group of employees whose job involves selling or promoting their company's products and services. sales promotion: a short-term marketing strategy used to boost immediate sales, increase demand, or introduce products by providing incentives to consumers, retailers, or salespeople

## Slide 61: Demand Forecasting
(I)Qualitative Methods
Jury of Executive Opinion Method
Delphi Method

## Slide 62: Jury of Executive Opinion Method
  Involves soliciting the opinions of a group of managers on expected future sales and combining them into a sales estimate.
  Advantages:
  Expeditious
  Variety of factors involved
  Immense appeal to managers who tend to prefer their judgment
Notes: Expeditious: done with speed and efficiency.

## Slide 63: Delphi Method
  Used for eliciting the opinions of a group of experts with the help of a mail survey.
  Experts are send the questionnaire by mail & asked to express their views
  Responses are summarized without disclosing identity, in case of extreme view, further reasons are asked in second round
  Continued for one or more round till a reasonable agreement emerges in the view of the experts
Notes: Elicit: manage to get information.

## Slide 64: Demand Forecasting
(II)Time Series Projection Method
Trend Projection Method
Exponential Smoothing Method
Moving Average Method

## Slide 65: Trend projection method
  Involves
  Determining the trend of consumption by analyzing past consumption statistics
  Projecting future trends by extrapolating the trends
  The linear relationship is used to find out the projected demand
  Yt = a + bt

## Slide 66: Moving Average Method
  The forecast for the next period is equal to the average of sales for several preceding periods
  Ft+1 = (St + St-1 + …..+St-n+1)/ n
  Ft+1 = Forecast for the next period
  St = Sales for the current period
  n = Number of Preceding years
.

## Slide 67: Demand Forecasting
(III)Casual Methods
Seek to develop forecasts based on cause-effect relationship
Chain Ratio Method
Consumption Level Method
End-use Method
Bass Diffusion Method
Leading Indicator Method
Econometric Method

## Slide 68: Chain Ratio Method
  The potential sales of a product may be estimated by applying a series of factors to a measure of aggregate demand.
  It uses a simple analytical approach to demand estimation. However, its reliability is critically dependent on the ratios and rates of usage in the process of determining sales potential

## Slide 69: Consumption Level Method
Consumption level method: Useful for a product that is directly consumed; this method estimates consumption level based on elasticity coefficients, the important ones being the income elasticity of demand and the price elasticity of demand.
Estimates consumption level on the basis of elasticity coefficients, the important ones being the income elasticity & price elasticity of demand

## Slide 70: End-use method
Suitable for estimating the demand for intermediate products, also called the consumption coefficient method.
Required key inputs are:
Projected output levels of consuming industries, and
Consumption Coefficient

## Slide 71: Bass Diffusion Method (Frank Bass)
p: The Coefficient of Innovation
The likelihood that a potential customer would adopt the product because of its innovative features
q: The Coefficient of Imitation
The tendency of a potential customer to buy the product because many others have bought it.

## Slide 72: Leading Indicator Method
Leading indicators are variables that change ahead of other variables, the lagging variables.
eg. Change in the level of urbanization (leading indicator) may be used to predict a change in the demand of air conditioners (lagging indicator)

## Slide 73: Econometric method
An econometric model is a mathematical representation of economic relationship(s) derived from economic theory.
Two types of models are employed:
Single Equation Model
Simultaneous Equation Model

## Slide 74: Single Equation Model
One variable, the dependent variable (Explained variable), is influenced by one or more independent variables (Explanatory variable).
Dt = a0 + a1Pt + a2Nt
Dt = Demand for a certain product in year t
Pt= Price for the product in year t
Nt= Income in year t

## Slide 75: Simultaneous Equation Model
Portrays economic relationship in terms of two or more equations.
GNPt = Gt + It + Ct
It = a0 + a1GNPt
Ct = b0 + b1GNPt
where: Gt = Government purchases for the year
It = Gross investment for the year
Ct = Consumption for the year t

## Slide 76: Topic Objectives & Outcome
s.no. | topic | outcomes
1 | To understand the Concepts and Types of Project Risks | CO2

## Slide 77: Project Risk & Uncertainty
A risk is defined as “an uncertain event or condition that, if it occurs, has a positive or negative effect on a project's objectives” (PMI, 2004). It must be emphasized that a risk is characterized by having both a consequence and a probability.
An uncertainty is defined as “the difference between the amount of information required to perform the task and the amount of information already possessed by the organization” (Galbraith, 1977).

## Slide 78: Project Risk
A formal, comprehensive project risk plan allows the project manager to be proactive regarding the innumerable things that can and do go wrong with a project.
Project risk management begins early in the life cycle. A clear understanding of the risks that face the project must be established. The sources of project risk are almost limitless, emphasizing the need for a well-thought-out, detailed plan.
Typical examples include the loss of a key team member, weather emergencies, technical failures, and poor suppliers.

## Slide 79: Project Risk

## Slide 80: Types of Risk
To relate the risk categories to the levels of project objectives, the three categories are defined.
Operational Risks
Short-term strategic Risks
Long-term strategic Risks

## Slide 81: Operational Risk
Risks related to the operational objectives of the project. This means risks restricted to the direct results of the project—that is, its products.

## Slide 82: Short-term strategic Risks
Short-term strategic risks are risks related to the objectives for project owner's use of the project results after the project has been completed.
It may also mean the risk for first-order effects of the project—that is, risk for the effects that should be achieved for the target group or users.

## Slide 83: Long-term strategic Risks
Risks related to long-term strategic objectives of the project—in other words, risks related to the project purpose, or, the long-term objective that the project is meant to contribute to.

## Slide 84: Common Project Risk

## Slide 85: Criteria to Categories Risk
Operational criteria, used to evaluate whether a given risk element is long-term strategic, short-term strategic, or operational include the following:
The risk element is considered an operational risk when: the risk element is a risk to the project output (which should be specified in a project definition/delivery contract)—i.e., a risk to the project's ability to deliver.

## Slide 86: Criteria to Categories Risk
The risk element is a short-term strategic risk when: the risk element is a risk to a functionality not specified in the project definition/delivery contract, but is necessary to achieve the effects of the project (restricted to the first-order effects for the target group/users).

## Slide 87: Criteria to Categories Risk
The risk element is a long-term strategic risk when: the risk element is a risk to achieving the long-term objectives of the project, but not a risk of the two categories mentioned above (i.e., operational or short-term strategic risk).

## Slide 88: Topic Objectives & Outcome
s.no. | topic | outcomes
1 | To identify the project risk. | CO2
2 | To do the Risks Analysis of projects | C02

## Slide 89: Risk Identification & Analysis
The risk identification function should not be left to chance but should be explicitly covered in a number of project documents:
Statement of work (SOW),
Work breakdown structure (WBS),
Budget,
Schedule,
Acquisition plan, and
Execution plan.

## Slide 90: Risk Identification & Analysis
The full project team should be actively involved.
Potential risks should be identified by all members of the project team.
No criticism of any suggestion is permitted.
Any potential risk identified by anyone should be recorded, regardless of whether other members of the group consider it to be significant.
All potential risks identified by brainstorming should be documented and followed up by the integrated project team.

## Slide 91: Six Steps Process
Step 1: Make a List
Steps 2 & 3: Determine the Probability of Risk Occurrence and Negative Impact.
Step 4: Prevent or Mitigate the Risk
Step 5: Consider Contingencies
Step 6: Establish the Trigger Point

## Slide 92: Step 1: Make a List
Brainstorm. Making a list of potential risks to the project should not be an analysis but a formal brainstorming session, when all ideas are captured.
Involve everyone.
Take a holistic approach to establishing the list, as all types of risks will need to be identified and dealt with accordingly.

## Slide 93: Step 2 & step 3
If the risk becomes a reality, how badly will it damage the project? This is the next question that needs to be asked and answered.
If the risk becomes reality, how will it affect the budget, schedule, resource utilization, scope of work, and so on? The output of steps 2 and 3 results in a list of potential risks with corresponding values for probability and negative impact.

## Slide 94: Step 2 & step 3
The probability scale can be based on a range of 1 through 10, with 1 representing unlikely and 10 being very likely. Negative impact can be represented by the same scale or in budgetary impact:

## Slide 95: Step 4: Prevent or Mitigate the Risk
Some risks can be prevented; others can only be mitigated. Earthquakes or the retirement of an important stakeholder, for instance, cannot be prevented.
Kill the risk before it has a chance to grow and flourish, and you won’t have to deal with it again.
For example, if a vendor or supplier is targeted for your project and one of your team members has had previous dealings with the company and was not impressed, he will inform you that the supplier’s material deliveries are frequently late and often rejected. Assuming that the supplier is not a sole source (your only choice), you can prevent the risk by finding an alternate supplier that is more reliable.

## Slide 96: Step 5: Consider Contingencies
Contingencies represent the specific actions that will be taken if the risk occurs.
Here, you answer the question “If the risk becomes reality, what will we do”?
For example, if acceptance testing for a supplier’s widgets has been identified as medium to high risk and a test failure occurs, an appropriate contingency might be to supply engineering support at the vendor’s expense. Another contingency might be to switch to another predetermined vendor if he has widgets in stock.
If the risk is a high priority (high probability, high negative impact) you will want to identify multiple contingencies.
If the risk falls in the middle range of the prioritization scale, you should establish at least one contingency.

## Slide 97: Step 6: Establish the Trigger Point
The trigger point is the point at which the risk becomes enough of a reality that the project manager needs to trigger the contingency.
The trigger point is often the most important element of the project risk plan. There is a direct relationship between the trigger point and the contingencies.
Trigger too soon and you will probably spend time, effort, or money for no good reason. Trigger too late and you may end up experiencing the full impact of the occurrence, with little value added by implementing the contingency.

## Slide 98: Risk Screening

## Slide 99: Risk Matrix
A useful tool when managing many risks across projects is the standard risk matrix.
Once the threats have been plotted onto the risk matrix, an H-M-L prioritization can be applied where the highest priority risks are positioned toward the upper right corner and lower priority ones toward the lower left.

## Slide 100: Risk Register
The risk register is a useful tool in managing actions taken regarding accepted risks to the project.
The risk register is the last ingredient of the project risk plan. The risk register also helps you identify ownership of contingency implementation, outcomes of actions taken, and active and inactive risks.

## Slide 101: Pareto diagram

## Slide 102: Failure Modes and Effects Analysis
In project risk assessment, a failure can be any significant event that the sponsor does not want to happen—a budget overrun, a schedule overrun, or a failure to meet scope, quality, or mission performance objectives.
The objective of failure modes and effects analysis is the identification of root or common causes, which may affect the project as a whole.

## Slide 103: Project Definition Rating Index
It includes detailed descriptions of issues and a weighted checklist of project scope definition elements to jog the memory of project team participants.
It provides the means to assess risk at various stages during the front-end project planning process and to focus efforts on high-risk areas that need additional definition.

## Slide 104: Quantitative Risk Analysis
Multivariate Statistical Models:
These methods are objective in that they do not rely on subjective probability distributions elicited from (possibly biased) project advocates.
Analysts build linear or nonlinear statistical models based on data from multiple past projects and then compare the project in question to the models.

## Slide 105: Quantitative Risk Analysis
Event Trees:
The results of the evaluations are the probabilities of various outcomes from given faults or failures.
Each event tree shows a particular event at the top and the conditions causing that event, leading to the determination of the likelihood of these events.
These methods can be adapted to project cost, schedule, and performance risk assessments.

## Slide 106: Quantitative Risk Analysis
Sensitivity Analysis:
A sensitivity coefficient is a derivative: the change in some outcome concerning a change in some input.
Even if the probability of a particular risk cannot be determined precisely, sensitivity analysis can be used to determine which variables have the greatest influence on the risk.

## Slide 107: Topic Objectives & Outcome
s.no. | topic | outcomes
1 | To learn the Risks Mitigation Strategies. | CO2

## Slide 108: Risk Identification Analysis

## Slide 109: Risk Identification Analysis
1. Include risk management in your projects
2. Communicate risks to others
3. Prioritize risks
4. Analyze risks
5. Implement risk responses as early as possible
6. Track them down regularly

## Slide 110: Risk Identification Analysis

## Slide 111: Daily quiz
Discuss the project identification.
Explain the idea generation process.
Explain various sources of secondary data.
Describe the chain ratio method of demand forecasting.
Discuss the methodology of the Delphi Technique.
Describe the types of risks associated with projects.
Explain various risk mitigation strategies in project management
Discuss the process of identifying the risk associated to project.

## Slide 112: Weekly assignment
Q1. Describe the identification and generation of ideas in project management.
Q2. Describe the market and demand analysis techniques for project management.
Q3. Describe various types of risks associated with project management.
Q4. Describe various risk mitigation strategies in project management.

## Slide 113: Topic links
https://www.youtube.com/watch?v=dAJy-3A6lPM
https://www.youtube.com/watch?v=4Or352bDQd4
https://www.youtube.com/watch?v=a0pAWPrKiGk

## Slide 114: MCQs
Q1. ETIG stands for.
Economic times intelligence group
Economic, Technological, Implementation, Governance
Early Times investigation group
None of the above
Q2. The market survey can be a.
Census survey
Sample survey
Both A & B
None of the above

## Slide 115: MCQs
Q3. In market survey, a sample of _______is contacted or observed.
Population
Sample Frame
Universe
None of the Above
Q4. Which of the following attributes of the questionnaire has an impact on the results of the market survey?
A. Quality
B. Adequate questions
C. Accuracy
D. All of the above

## Slide 116: MCQs
Q5. Bass Diffusion method was developed by.
Frank Bass
Huses Bass
Pascal
Devorak
Q6. Leading indicators are the variables that change ______of the other variables.
Ahead
After
Simultaneously
None of these

## Slide 117: Old question paper

## Slide 118: Old question paper

## Slide 119: Old question paper

## Slide 120: Old question paper

## Slide 121: Old question paper

## Slide 122: Old question paper

## Slide 123: Expected Questions
Q1. Describe the situational analysis.
Q2. Discuss the demand analysis. Explain various demand forecasting techniques used in demand analysis.
Q3. Explain the project risk. Discuss various categories of the project risks.
Q4. Explain various risk mitigation strategies that are used in project risk management.

## Slide 124: References
Books:
Larsen, E.W., Gray C.F., & Joshi, R. (2021). Project management: The Managerial process. McGraw Hill.
Chandra, P. (2019). Projects: Planning, Analysis, Selection, Financing, Implementation and Review. McGraw Hill.
REFERENCE BOOK:
Nagarajan, K. (2017). Project Management. New Age International Pvt. Ltd.
Paneerselvam, R., & Senthilkumar, P. (2013). Project Management. Prentice Hall India Learning Pvt. Ltd.
Pinto, J.K. (2020). Project Management. Global EduTech.
Desai, V. (2016). Project Management. Himalaya Publishing House.

## Slide 125: Recap of unit
A risk is defined as “an uncertain event or condition that, if it occurs, has a positive or negative effect on a project's objectives”
The project idea must be compatible with the interest, personality & resources of an entrepreneur
Project Identification is often the outcome of TRIGGERING PROCESSES / EVENTS rather than an analytical exercise.
To tap the creativity of the people and to harness their entrepreneurial urges, a conducive organizational climate has to be fostered.
Some kind of preliminary screening is required to eliminate ideas which prima facie are not promising